Project 1: Organizing and Summarizing Air Quality

Client: UNMC Water, Climate and Health Group

Project Team: Mohamed Adam

Date Submitted: 1/30/26

Project Goals:

This aim of this project is to analyze air quality data collected across the state of Nebraska between February 2024 and March 2025. UNMC Water, Climate and Health Group requires an evaluation of the quality conditions to determine whether the air quality values match the ones required by the National Ambient Air Quality Standards (NAAQS) and to resolve any possible public health concerns

Specifically, this project aims to:
1. Identify the locations with the highest mean and median concentrations of VOC, PM 2.5, and PM 10.0

2. Find out where the maximum pollutant values occurred

3. Analyze the air quality with several environmental factors like temperature, humidity, elevation, and geographic location

4. Evualuate whether any locations had AQI levels that were unhealthy for the population

5. Provide research based explanations for trends and extreme outliers

Project Tasks:

Task 1: Data Acquisition and Organization

The team will obtain air quality data from AirPurple. Raw data files will be interpreted in CSV format and used in Python code. Data cleaning will check for missing values, standardizing column names, confirming units, and formatting dates.

Task 2: Data Processing and Statistical Analysis

Python coding will be used to analyze the dataset. The mean, median, and max values of VOC, PM 2.5, and PM 10.0 will be determined at each sensor location. The results will then be grouped by sensor. Dates and locations will also be provided for max pollutant concentrations outbreaks

Task 3: Environmental and AQI Evaluation:
 Humidity and temperature data will be categorized. The team will analyze the effects of how humidity and temperature impact the air quality values.  EPA AQI guidelines will also help determine whether any locations experienced and provided public health risks

Task 4: Research:
Research will be conducted to provide explanations using evidence to make conclusions on the data. The research will focus on air quality trends, maximum values, and AQI rules.

Task 5: Documentation
Python code will be written in a Jupyter Notebook and an annotated code document explaining every step of the analysis will be provided to the client. A written report summary will also be provided along with a GitHub repository containing the code and data.

| Deliverable | Description |
| --- | --- |
| CIVE202_Spring2026_MohamedAdam_Project1_RawData.csv | This file contains the original air quality data used in the analysis. |
| CIVE202_Spring2026_MohamedAdam_Project1_Analysis.ipynb | This Jupyter Notebook contains all the Python code used to clean, process, and analyze the data |
| CIVE202_Spring2026_MohamedAdam_Project1_Analysis.ipynb CIVE202_Spring2026_MohamedAdam_Project1_RawData.csv CIVE202_Spring2026_MohamedAdam_Project1_README.md | This GitHub repository will include all the project files, data, code, and documentation. The README includes a small summary of everything |
| CIVE202_Spring2026_MohamedAdam_Project1_AnnotatedCode.docx | This document explains each Python code section in detail and the purpose and function behind it |
| CIVE202_Spring2026_MohamedAdam_Project1_FinalReport.docx | This word document summarizes the project background, method, results, and discussion in one report. |
| CIVE202_Spring2026_MohamedAdam_Project1_ScopeOfWork.docx | This is a scope of work that defines the goals, tasks, deliverables, and outlines when the work will be completed to the client’s requests. |

All deliverables will be submitted by Tuesday, February 3rd, 2026